## Personal Journal
Team Journal
Team (number and name): zioFrank (7 membri)
When (Month/Day) |  | Time spent | Partners (please report how many people have been working) | Brief Description of the performed task | Category | Sub-Category | Deliverable | Total Time
11 | 30 | 2h | 7 | Brainstorming | Learning | Requirements engineering | Deliverable 1 | 34.30
12 | 1 | 2h | 7 | Discovering requirements | Doing | Requirements elicitation
12 | 2 | 2.30h | 7 | Discovering requirements | Doing | Requirements priority
12 | 2 | 2h | 7 | Bozza diagramma E/R | Doing | DB modeling
12 | 3 | 4h | 7 | Development use case | Doing | Use case diagram
12 | 4 | 2h | 7 | Development Analisys Obj Model | Doing | Analisys Model
12 | 7 | 2h | 7 | Componets analysis | Learning | Component diagram
12 | 7 | 2h | 3 | Starting Components Diagram | Doing | Component diagram
12 | 9 | 4h | 7 | Restyling Components Diagram | Doing | Component diagram
12 | 9 | 2h | 3 | Development Class Diagram | Doing | Class diagram
12 | 9 | 2h | 4 | Development Sequence Diagram | Doing | Sequence diagram
12 | 10 | 4h | 6 | Documentation Diagram & Review | Doing | Documentation
12 | 11 | 4h | 5 | Documentation Diagram & Review | Doing | Documentation
12 | 16 | 4h | 5 | Brainstorming | Learning | Restyling | Deliverable 2 | 32
12 | 17 | 2h | 5 | Tecnology Discovery | Learning | Tool
12 | 21 | 2h | 7 | Decision Design | Doing | Restyling
12 | 21 | 2h | 4 | Restyling Use Case Diagram | Doing | Restyling
12 | 21 | 2h | 3 | Restyling Components Diagram | Doing | Restyling
12 | 22 | 2h | 3 | Restyling Use Case Diagram | Doing | Restyling
12 | 22 | 2h | 4 | Restyling Class Diagram | Doing | Restyling
12 | 22 | 1h | 7 | Risk Discovery and Variability Decision | Doing | Restyling
12 | 24 | 2h | 2 | Documentation Diagram & Review | Doing | Restyling
12 | 26 | 1h | 2 | Documentation Diagram & Review | Doing | Restyling
12 | 27 | 3h | 2 | Documentation Diagram & Review | Doing | Restyling
12 | 28 | 2h | 7 | Brainstorming | Learning | Restyling
12 | 28 | 7h | 3 | Documentation Diagram & Review | Doing | Restyling
1 | 7 | 1h | 6 | Brainstoarming | Doing | Design | Deliverable 3 | 55
1 | 8 | 2h | 3 | Lenguage & Tools | Learning | Tool
1 | 11 | 1h | 4 | Binding | Doing | Revisioning
1 | 11 | 4h | 6 | Algorithms & O.O. | Learning | Lenguage
1 | 12 | 5h | 6 | GUI & Design | Doing | Design
1 | 13 | 1h | 3 | Binding | Doing | Revisioning
1 | 13 | 6h | 6 | Code & Design | Doing & Learning | Design
1 | 14 | 6h | 6 | Algorithms & O.O. | Learning | Lenguage
1 | 18 | 1h | 3 | Binding | Doing | Revisioning
1 | 18 | 4h | 6 | Algorithms & DB Restyling | Doing & Learning | Design
1 | 19 | 5h | 6 | Code & GUI Restyling | Doing | Design
1 | 20 | 2h | 3 | Binding | Doing | Revisioning
1 | 20 | 7h | 6 | Code & Documentation | Doing | Documentation
1 | 21 | 10h | 6 | Documentation | Doing | Documentation